## Model
Room construction project
Data on activity network
Activity | Index | Predecessors | Duration
Prepare foundation | A | None | 4
Put up frame | B | A | 4
Order custom windows | C | None | 11
Erect outside walls | D | B | 3
Do electrical wiring | E | D | 4
Do plumbing | F | D | 3
Put in duct work | G | D | 4
Hang dry wall | H | E,F,G | 3
Install windows | I | B,C | 1
Paint and clean up | J | H | 2
Node event times |  |  | Arcs (activitities), corresponding nodes, and time constraints
Node | Time |  | Activity | StartNode | EndNode | EndTime |  | StartTime + Duration
1 | 0 |  | A | 1 | 2 | 4 | >= | 4 | *
2 | 4 |  | B | 2 | 3 | 8 | >= | 8 | *
3 | 8 |  | B | 2 | 4 | 19 | >= | 8
4 | 19 |  | C | 1 | 4 | 19 | >= | 11
5 | 11 |  | D | 3 | 5 | 11 | >= | 11 | *
6 | 15 |  | E | 5 | 6 | 15 | >= | 15 | *
7 | 18 |  | F | 5 | 6 | 15 | >= | 14
8 | 20 |  | G | 5 | 6 | 15 | >= | 15
|  |  | H | 6 | 7 | 18 | >= | 18 | *
|  |  | I | 4 | 8 | 20 | >= | 20
|  |  | J | 7 | 8 | 20 | >= | 20 | *
Project time | 20
Activities with asterisks next to them have positive shadow prices in the sensitivity report. They are on the critical path.
Range names used: LTable1 - B5:D14 LTable2 - A18:B25 EventTimes - B19:B25 EndTimes - G18:G28 StTimesPlusDurs - I18:I28 ProjTime - B30

## Sensitivity Report 1
Microsoft Excel 9.0 Sensitivity Report
Worksheet: [Project1.xls]Sheet1
Report Created: 1/24/00 4:23:49 PM
Adjustable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $B$19 | Time | 4 | 0 | 0 | 1e+30 | 1
| $B$20 | Time | 8 | 0 | 0 | 1e+30 | 1
| $B$21 | Time | 19 | 0 | 0 | 0 | 1
| $B$22 | Time | 11 | 0 | 0 | 1e+30 | 1
| $B$23 | Time | 15 | 0 | 0 | 1e+30 | 1
| $B$24 | Time | 18 | 0 | 0 | 1e+30 | 1
| $B$25 | Time | 20 | 0 | 1 | 1e+30 | 1
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $G$18 | A EndTime | 4 | 1 | 0 | 1e+30 | 4
| $G$19 | B EndTime | 8 | 1 | 0 | 1e+30 | 8
| $G$20 | B EndTime | 19 | 0 | 0 | 11 | 1e+30
| $G$21 | C EndTime | 19 | 0 | 0 | 8 | 1e+30
| $G$22 | D EndTime | 11 | 1 | 0 | 1e+30 | 8
| $G$23 | E EndTime | 15 | 1 | 0 | 1e+30 | 0
| $G$24 | F EndTime | 15 | 0 | 0 | 1 | 1e+30
| $G$25 | G EndTime | 15 | 0 | 0 | 0 | 1e+30
| $G$26 | H EndTime | 18 | 1 | 0 | 1e+30 | 8
| $G$27 | I EndTime | 20 | 0 | 0 | 8 | 1e+30
| $G$28 | J EndTime | 20 | 1 | 0 | 1e+30 | 8