## Model
Room construction project with crashing
Data on activity network | [5 empty] | Crashing constraints
Activity | Index | Predecessors | Duration | Cost/day |  | Reduction |  | Max reduction
Prepare foundation | A | None | 4 | 150 |  | 2 | <= | 2
Put up frame | B | A | 4 | 160 |  | 0 | <= | 2
Order custom windows | C | None | 11 | 80 |  | 0 | <= | 4
Erect outside walls | D | B | 3 | 80 |  | 1 | <= | 1
Do electrical wiring | E | D | 4 | 160 |  | 0 | <= | 2
Do plumbing | F | D | 3 | 150 |  | 0 | <= | 1
Put in duct work | G | D | 4 | 130 |  | 0 | <= | 2
Hang dry wall | H | E,F,G | 3 | 100 |  | 1 | <= | 1
Install windows | I | B,C | 1 | 70 |  | 0 | <= | 0.5
Paint and clean up | J | H | 2 | 100 |  | 1 | <= | 1
Node event times |  |  | Arcs (activitities), corresponding nodes, and time constraints
Node | Time |  | Activity | StartNode | EndNode | EndTime |  | StartTime + Duration
1 | 0 |  | A | 1 | 2 | 2 | >= | 2 | *
2 | 2 |  | B | 2 | 3 | 6 | >= | 6 | *
3 | 6 |  | B | 2 | 4 | 14 | >= | 6
4 | 14 |  | C | 1 | 4 | 14 | >= | 11
5 | 8 |  | D | 3 | 5 | 8 | >= | 8 | *
6 | 12 |  | E | 5 | 6 | 12 | >= | 12 | *
7 | 14 |  | F | 5 | 6 | 12 | >= | 11
8 | 15 |  | G | 5 | 6 | 12 | >= | 12
|  |  | H | 6 | 7 | 14 | >= | 14 | *
|  |  | I | 4 | 8 | 15 | >= | 15
|  |  | J | 7 | 8 | 15 | >= | 15 | *
Deadline constraint | 15 | <= | 15
Total cost | 580
Range names used: LTable1 - B5:G14 UnitCosts - E5:E14 Reductions - G5:G14 MaxReds - I5:I14 LTable2 - A18:B25 EventTimes - B19:B25 EndTimes - G18:G28 StTimesPlusDurs - I18:I28 ProjTime - B30 Deadline - D30 TotalCost - B32
Activities with asterisks next to them have positive shadow prices in the sensitivity report. They are on the critical path.

## Sensitivity Report 1
Microsoft Excel 9.0 Sensitivity Report
Worksheet: [Crashing.xls]Model
Report Created: 1/25/00 2:01:21 PM
Adjustable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $G$5 | None Reduction | 2 | -10 | 150 | 10 | 1e+30
| $G$6 | A Reduction | 0 | 0 | 160 | 1e+30 | 0
| $G$7 | None Reduction | 0 | 80 | 80 | 1e+30 | 80
| $G$8 | B Reduction | 1 | -80 | 80 | 80 | 1e+30
| $G$9 | D Reduction | 0 | 0 | 160 | 0 | 10
| $G$10 | D Reduction | 0 | 150 | 150 | 1e+30 | 150
| $G$11 | D Reduction | 0 | 130 | 130 | 1e+30 | 130
| $G$12 | E,F,G Reduction | 1 | -60 | 100 | 60 | 1e+30
| $G$13 | B,C Reduction | 0 | 70 | 70 | 1e+30 | 70
| $G$14 | H Reduction | 1 | -60 | 100 | 60 | 1e+30
| $B$19 | Time | 2 | 0 | 0 | 1e+30 | 10
| $B$20 | Time | 6 | 0 | 0 | 0 | 10
| $B$21 | Time | 14 | 0 | 0 | 0 | 70
| $B$22 | Time | 8 | 0 | 0 | 0 | 10
| $B$23 | Time | 12 | 0 | 0 | 60 | 1e+30
| $B$24 | Time | 14 | 0 | 0 | 60 | 1e+30
| $B$25 | Time | 15 | 0 | 0 | 160 | 1e+30
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $G$18 | A EndTime | 2 | 160 | 0 | 0 | 0
| $G$19 | B EndTime | 6 | 160 | 0 | 0 | 0
| $G$20 | B EndTime | 14 | 0 | 0 | 8 | 1e+30
| $G$21 | C EndTime | 14 | 0 | 0 | 3 | 1e+30
| $G$22 | D EndTime | 8 | 160 | 0 | 0 | 0
| $G$23 | E EndTime | 12 | 160 | 0 | 2 | 0
| $G$24 | F EndTime | 12 | 0 | 0 | 1 | 1e+30
| $G$25 | G EndTime | 12 | 0 | 0 | 0 | 1e+30
| $G$26 | H EndTime | 14 | 160 | 0 | 0 | 0
| $G$27 | I EndTime | 15 | 0 | 0 | 3 | 1e+30
| $G$28 | J EndTime | 15 | 160 | 0 | 0 | 0
| $B$30 | ProjTime | 15 | -160 | 15 | 0 | 0