## Sheet1
Problem 5.44 | [7 empty] | Ranges names
[8 empty] | EndTimes | =Sheet1!$G$18:$G$27
Data on activity network (see network graph below) | [7 empty] | EventTimes | =Sheet1!$B$19:$B$24
Activity | Index | Predecessors | Duration |  |  |  |  | LTable1 | =Sheet1!$B$5:$D$14
Find site | A | None | 3 |  |  |  |  | LTable2 | =Sheet1!$A$18:$B$24
Find engineers | B | A | 2 |  |  |  |  | ProjTime | =Sheet1!$B$27
Hire opening act | C | A | 6 |  |  |  |  | StTimesPlusDurs | =Sheet1!$I$18:$I$27
Set radio and TV ads | D | C | 2 |  |  |  |  | Times | =Sheet1!$B$19:$B$24
Set up ticket agents | E | A | 3
Prepare electronics | F | B | 3
Print advertising | G | C | 5
Set up transportation | H | C | 1
Rehearsals | I | F,H | 1.5
Last-minute details | J | I | 2
Network node times |  |  | Arcs (activities), corresponding to nodes, and time constraints
Node | Time |  | Activity | StartNode | EndNode | EndTime |  | StartTime+Duration
1 | 0 |  | A | 1 | 2 | 3 | >= | 3 | *
2 | 3 |  | B | 2 | 3 | 7.5 | >= | 5
3 | 7.5 |  | C | 2 | 4 | 9 | >= | 9 | *
4 | 9 |  | D | 4 | 7 | 14 | >= | 11
5 | 10.5 |  | E | 2 | 7 | 14 | >= | 6
6 | 12 |  | F | 3 | 5 | 10.5 | >= | 10.5
7 | 14 |  | G | 4 | 7 | 14 | >= | 14 | *
|  |  | H | 4 | 5 | 10.5 | >= | 10
|  |  | I | 5 | 6 | 12 | >= | 12
Project time | 14 |  | J | 6 | 7 | 14 | >= | 14
Critical path | A-C-G