## Pump
Project Management
| Solve |  | Show Critical |  |  | Schedule
| Change |  | Graph | [20 empty] | Activity on Node Network
[24 empty] | Sorted Activity Nodes | [10 empty] | Sorted Precedence Arcs
|  |  |  | Activity Data |  |  | Activity Time Estimates | [14 empty] | Difference | 0.001 |  |  |  |  | Early | Late | Early | Late | Critical |  |  |  | From | To | From | To | Critical
[8 empty] | Most |  |  |  |  | Time |  |  | Resources |  | Early | Late | Early | Late |  | Near | Index | Sort | Name | Time | Start | Start | Finish | Finish | Node | Level | Depth | Index | Index | Index | Name | Name | Arc
|  |  |  | Critical | Name | Description | Min. | Likely | Max. | Mean | S.D. | Var. | Hours | Predecessors |  | Crew | Sort | Start | Start | Finish | Finish | Slack | Critical | 1 | 1 | Start | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | Start | A | 1
Critical Path |  |  | 1 | 1 | A | POUR SLAB | 9 | 11 | 19 | 12 | 1.6667 | 2.7778 | 12 |  |  | 4 | 2 | 0 | 0 | 12 | 12 | 0 | 1 | 2 | 2 | A | 12 | 0 | 0 | 12 | 12 | 1 | 1 | 0 | 2 | 1 | 3 | Start | B | 0
Exp. Time | 57 | Hours | 2 | 0 | B | ORDER PUMP UNIT | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0.25 |  |  | 1 | 3 | 0 | 27.75 | 0.25 | 28 | 27.75 | 0 | 3 | 3 | B | 0.25 | 0 | 27.75 | 0.25 | 28 | 0 | 1 | 1 | 3 | 1 | 4 | Start | C | 0
Var. Time | 12.5 |  | 3 | 0 | C | CUT PATH | 20 | 30 | 40 | 30 | 3.3333 | 11.1111 | 30 |  |  | 6 | 4 | 0 | 9.6667 | 30 | 39.6667 | 9.6667 | 0 | 4 | 4 | C | 30 | 0 | 9.6667 | 30 | 39.6667 | 0 | 1 | 2 | 4 | 2 | 5 | A | D | 1
SD. Time | 3.5355 | Hours | 4 | 1 | D | CURE SLAB | 24 | 24 | 24 | 24 | 0 | 0 | 24 | A |  | 0 | 5 | 12 | 12 | 36 | 36 | 0 | 1 | 5 | 5 | D | 24 | 12 | 12 | 36 | 36 | 1 | 2 | 0 | 5 | 3 | 6 | B | E | 0
|  |  | 5 | 0 | E | DELIVER UNIT | 3 | 9 | 9 | 8 | 1 | 1 | 8 | B |  | 0 | 6 | 0.25 | 28 | 8.25 | 36 | 27.75 | 0 | 6 | 6 | E | 8 | 0.25 | 28 | 8.25 | 36 | 0 | 2 | 1 | 6 | 4 | 7 | C | F | 0
Due | 59 | Hours | 6 | 0 | F | RUN FLOW LINE | 10 | 11 | 14 | 11.3333 | 0.66667 | 0.44444 | 11.3333 | C |  | 6 | 7 | 30 | 39.6667 | 41.3333 | 51 | 9.6667 | 0 | 7 | 7 | F | 11.3333 | 30 | 39.6667 | 41.3333 | 51 | 0 | 2 | 2 | 7 | 4 | 8 | C | G | 0
Probability | 0.7142 |  | 7 | 0 | G | RUN ELECTRIC LINE | 8 | 10 | 12 | 10 | 0.66667 | 0.44444 | 10 | C |  | 3 | 8 | 30 | 41 | 40 | 51 | 11 | 0 | 8 | 8 | G | 10 | 30 | 41 | 40 | 51 | 0 | 2 | 3 | 8 | 5 | 9 | D | H | 1
|  |  | 8 | 1 | H | MOUNT UNIT | 4 | 5 | 12 | 6 | 1.3333 | 1.7778 | 6 | D | E | 3 | 9 | 36 | 36 | 42 | 42 | 0 | 1 | 9 | 9 | H | 6 | 36 | 36 | 42 | 42 | 1 | 3 | 0 | 9 | 6 | 9 | E | H | 0
|  |  | 9 | 0 | I | INSTALL ELECTRIC MOTOR | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4 | H |  | 2 | 10 | 42 | 47 | 46 | 51 | 5 | 0 | 10 | 10 | I | 4 | 42 | 47 | 46 | 51 | 0 | 4 | 0 | 10 | 7 | 13 | F | L | 0
|  |  | 10 | 1 | J | RUN SUCKER RODS | 4 | 8 | 18 | 9 | 2.3333 | 5.4444 | 9 | H |  | 3 | 11 | 42 | 42 | 51 | 51 | 0 | 1 | 11 | 11 | J | 9 | 42 | 42 | 51 | 51 | 1 | 4 | 1 | 11 | 8 | 12 | G | K | 0
|  |  | 11 | 0 | K | TIE IN, TEST MOTOR | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | G | I | 1 | 12 | 46 | 51 | 47.5 | 52.5 | 5 | 0 | 12 | 12 | K | 1.5 | 46 | 51 | 47.5 | 52.5 | 0 | 5 | 0 | 12 | 9 | 10 | H | I | 0
|  |  | 12 | 1 | L | NIPPLE UP WELL HEAD | 1 | 1 | 4 | 1.5 | 0.5 | 0.25 | 1.5 | F | J | 2 | 13 | 51 | 51 | 52.5 | 52.5 | 0 | 1 | 13 | 13 | L | 1.5 | 51 | 51 | 52.5 | 52.5 | 1 | 5 | 1 | 13 | 9 | 11 | H | J | 1
|  |  | 13 | 1 | M | TEST PUMP | 1 | 4 | 10 | 4.5 | 1.5 | 2.25 | 4.5 | K | L | 2 | 14 | 52.5 | 52.5 | 57 | 57 | 0 | 1 | 14 | 14 | M | 4.5 | 52.5 | 52.5 | 57 | 57 | 1 | 6 | 0 | 14 | 10 | 12 | I | K | 0
|  |  | 14 | 0 | N | OPEN VALUES | 0.12 | 1 | 2 | 1.02 | 0.31333 | 0.098178 | 1.02 | K | L | 1 | 15 | 52.5 | 55.98 | 53.52 | 57 | 3.48 | 0 | 15 | 15 | N | 1.02 | 52.5 | 55.98 | 53.52 | 57 | 0 | 6 | 1 | 15 | 11 | 13 | J | L | 1
[24 empty] | 16 | 16 | End | 0 | 57 | 57 | 57 | 57 | 1 | 7 | 0 | 16 | 12 | 14 | K | M | 0
[13 empty] | Num. Predecessors | 16 | [20 empty] | 17 | 12 | 15 | K | N | 0
[35 empty] | 18 | 13 | 14 | L | M | 1
[35 empty] | 19 | 13 | 15 | L | N | 0
[35 empty] | 20 | 14 | 16 | M | End | 1
[35 empty] | 21 | 15 | 16 | N | End | 0

## Pump_Schedule
Schedule Pump
Search
Bucket | 1 | Hours |  | Activities
[9 empty] | Early | Late |  | Activity | Sched. | Sched. | Resources |  | Time
Project |  |  |  | Index | Sort | Name | Description | Time | Start | Start | Slack | Delay | Start | Finish | Crew | Color | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68
Completion Time |  |  |  | 1 | 1 | Start | Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max Delay | 0 | Hours |  | 2 | 2 | A | POUR SLAB | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay Unit Cost | 1 | /Hours |  | 3 | 3 | B | ORDER PUMP UNIT | 0.25 | 0 | 27.75 | 27.75 | 0 | 0 | 0.25 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earliest | 57 | Hours |  | 4 | 4 | C | CUT PATH | 30 | 0 | 9.6667 | 9.6667 | 1 | 1 | 31 | 6 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled | 57 | Hours |  | 5 | 5 | D | CURE SLAB | 24 | 12 | 12 | 0 | 0 | 12 | 36 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shortage | Shortage | 6 | 6 | E | DELIVER UNIT | 8 | 0.25 | 28 | 27.75 | 0 | 0.25 | 8.25 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resources | Avail. | Unit Cost | Cost | 7 | 7 | F | RUN FLOW LINE | 11.3333 | 31 | 39.6667 | 8.6667 | 0 | 31 | 42.3333 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crew | 8 | 1 | 31 | 8 | 8 | G | RUN ELECTRIC LINE | 10 | 31 | 41 | 10 | 10 | 41 | 51 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | 9 | H | MOUNT UNIT | 6 | 36 | 36 | 0 | 0 | 36 | 42 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Costs |  |  |  | 10 | 10 | I | INSTALL ELECTRIC MOTOR | 4 | 42 | 47 | 5 | 0 | 42 | 46 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delay | 0 |  |  | 11 | 11 | J | RUN SUCKER RODS | 9 | 42 | 42 | 0 | 0 | 42 | 51 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shortage | 31 |  |  | 12 | 12 | K | TIE IN, TEST MOTOR | 1.5 | 51 | 51 | 0 | 0 | 51 | 52.5 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 31 |  |  | 13 | 13 | L | NIPPLE UP WELL HEAD | 1.5 | 51 | 51 | 0 | 0 | 51 | 52.5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | 14 | M | TEST PUMP | 4.5 | 52.5 | 52.5 | 0 | 0 | 52.5 | 57 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feasibility |  |  |  | 15 | 15 | N | OPEN VALUES | 1.02 | 52.5 | 55.98 | 3.48 | 0 | 52.5 | 53.52 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Late | 0 |  |  | 16 | 16 | End | End | 0 | 57 | 57 | 0 | 0 | 57 | 57 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule | 0 | [13 empty] | Resources
Feasible | TRUE | [13 empty] | Used | Crew | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 12 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Available | Crew | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
[15 empty] | Shortage | Crew | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Shortage Unit Cost | Crew | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[15 empty] | Shortage Cost | Crew | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0